## Asr info
CEF | Transport
Action Code | 2016-SK-TMC-0218-W
Exercise Year | 2023
Version | 1
Actual Action Start Date | 02/03/2017
Actual Action End Date | 30/06/2025
A. Maximum EU contribution (Art. 3) | €25,112,113.00
B. Pre-financing rate (Art. 4.1.2) | 50%
C. Maximum pre-financing payment (Art. 4.1.2) (=B*A) | €12,556,057.00
D. Maximum ceiling for the sum of pre-financing and interim payments (Art 4.1.3) (=80%*A) | €20,089,690.40
E. Sum of Previous Pre-financing Payments | €932,555.83
F. Sum of Interim Payments | €606,069.97
G. Sum of pre-financing and interim payments (E+F) | €1,538,625.80

## Eligible costs (€)
Update of the indicative breakdown of estimated eligible costs of the Action 2016-SK-TMC-0218-W (€)
|  |  | 2017 |  | 2018 |  | 2019 |  | 2020 |  | 2021 |  | 2022 |  | 2023 |  | 2024 |  | 2025 |  | Total
| Activity name | Funding rate (%) | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Lastest GA in force | Current ASR | Deviation (%)
| 1 Public procurement, authorisation procedures and detailed design | 85
1 | Železnice Slovenskej republiky |  | 0 | 0 | 0 | 0 | 737798 | 731900 | 906437 | 335100 | 463759 | 512000 | 0 | 21000 | 0 | 134000 | 0 | 0 | 0 | 0
Total for activity 1
| 2 Construction works and author supervision | 85
1 | Železnice Slovenskej republiky |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102343 | 0 | 409374 | 0 | 307031 | 297728 | 0 | 521020 | 0 | 0
Total for activity 2
| 3 Construction works | 85
1 | Železnice Slovenskej republiky |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1317496 | 0 | 10539968 | 0 | 14492456 | 15754411 | 0 | 23631648.89 | 0 | 0
Total for activity 3
| 4 Project management and communication | 85
1 | Železnice Slovenskej republiky |  | 0 | 0 | 15000 | 0 | 18000 | 0 | 18000 | 3500 | 70000 | 0 | 71000 | 7500 | 75000 | 127000 | 0 | 129000 | 0 | 0
Total for activity 4
Total eligible costs
1 | Železnice Slovenskej republiky
Total cumulated eligible costs
1 | Železnice Slovenskej republiky

## Financing needs (€)
Financing needs of the Action 2016-SK-TMC-0218-W (€)
|  |  | 2017 |  | 2018 |  | 2019 |  | 2020 |  | 2021 |  | 2022 |  | 2023 |  | 2024 |  | 2025 |  | Total
| Activity name | Funding rate (%) | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Lastest GA in force | Current ASR | Deviation (%)
1 Public procurement, authorisation procedures and detailed design
1 | Železnice Slovenskej republiky
Totals for activity 1
2 Construction works and author supervision
1 | Železnice Slovenskej republiky
Totals for activity 2
3 Construction works
1 | Železnice Slovenskej republiky
Totals for activity 3
4 Project management and communication
1 | Železnice Slovenskej republiky
Totals for activity 4
Total financing needs
1 | Železnice Slovenskej republiky
Total cumulated financing needs
1 | Železnice Slovenskej republiky

## Progress Overview
Progress Overview of the Action 2016-SK-TMC-0218-W (at accumulated level)
| 2017 |  |  | 2018 |  |  | 2019 |  |  | 2020 |  |  | 2021 |  |  | 2022 |  |  | 2023 |  |  | 2024 |  |  | 2025
| Financial Progress |  | Technical Progress | Financial Progress |  | Technical Progress | Financial Progress |  | Technical Progress | Financial Progress |  | Technical Progress | Financial Progress |  | Technical Progress | Financial Progress |  | Technical Progress | Financial Progress |  | Technical Progress | Financial Progress |  | Technical Progress | Financial Progress |  | Technical Progress
Activity name | Latest GA | Current ASR | Current ASR | Latest GA | Current ASR | Current ASR | Latest GA | Current ASR | Current ASR | Latest GA | Current ASR | Current ASR | Latest GA | Current ASR | Current ASR | Latest GA | Current ASR | Current ASR | Latest GA | Current ASR | Current ASR | Latest GA | Current ASR | Current ASR | Latest GA | Current ASR | Current ASR
Activity 1 | 0 | 0 | 9 | 0 | 0 | 23 | 35 | 42 | 35 | 78 | 62 | 48 | 100 | 91 | 70 | 100 | 92 | 89 | 100 | 100 | 98 | 100 | 100 | 100 | 100 | 100 | 100
Activity 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 62 | 0 | 0 | 100 | 36 | 8 | 100 | 100 | 75 | 100 | 100 | 100
Activity 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 45 | 0 | 0 | 100 | 40 | 38 | 100 | 100 | 100 | 100 | 100 | 100
Activity 4 | 0 | 0 | 0 | 6 | 0 | 20 | 12 | 0 | 30 | 19 | 1 | 60 | 45 | 1 | 60 | 72 | 4 | 60 | 100 | 52 | 60 | 100 | 100 | 60 | 100 | 100 | 100
For the Action | 0 | 0 | 3 | 0 | 0 | 8 | 3 | 2 | 12 | 6 | 3 | 17 | 12 | 4 | 24 | 50 | 4 | 30 | 100 | 42 | 51 | 100 | 100 | 93 | 100 | 100 | 100