## Asr info
CEF | Transport
Action Code | 2016-SK-TMC-0218-W
Exercise Year | 2023
Version | 1
Actual Action Start Date | 02/03/2017
Actual Action End Date | 2025-06-30
A. Maximum EU contribution (Art. 3) | €25,112,113.00
B. Pre-financing rate (Art. 4.1.2) | 50%
C. Maximum pre-financing payment (Art. 4.1.2) (=B*A) | €12,556,057.00
D. Maximum ceiling for the sum of pre-financing and interim payments (Art 4.1.3) (=80%*A) | €20,089,690.40
E. Sum of Previous Pre-financing Payments | €932,555.83
F. Sum of Interim Payments | €606,069.97
G. Sum of pre-financing and interim payments (E+F) | €1,538,625.80

## Eligible costs (€)
Update of the indicative breakdown of estimated eligible costs of the Action 2016-SK-TMC-0218-W (€)
|  |  | 2017 |  | 2018 |  | 2019 |  | 2020 |  | 2021 |  | 2022 |  | 2023 |  | 2024 |  | Total
| Activity name | Funding rate (%) | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Lastest GA in force | Current ASR | Deviation (%)
| 1 Public procurement, authorisation procedures and detailed design | 85
1 | Železnice Slovenskej republiky |  | 0 | 0 | 0 | 0 | 737798 | 731900 | 906437 | 335100 | 463759 | 512000 | 0 | 21000 | 0 | 134000 | 0 | 0 | 2107994 | 1734000 | -17.74%
|  | Total for activity 1 | 0 | 0 | 0 | 0 | 737798 | 731900 | 906437 | 335100 | 463759 | 512000 | 0 | 21000 | 0 | 134000 | 0 | 0 | 2107994 | 1734000 | -17.74%
| 2 Construction works and author supervision | 85
1 | Železnice Slovenskej republiky |  | 0 |  | 0 |  | 0 |  | 0 |  | 102343 |  | 409374 |  | 307031 | 297728 | 0 | 521020 | 818748 | 818748 | 0%
|  | Total for activity 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102343 | 0 | 409374 | 0 | 307031 | 297728 | 0 | 521020 | 818748 | 818748 | 0%
| 3 Construction works | 85
1 | Železnice Slovenskej republiky |  | 0 |  | 0 |  | 0 |  | 0 |  | 1317496 |  | 10539968 |  | 14492456 | 15754411 | 0 | 23631648.89 | 26349920 | 39386059.89 | 49.47%
|  | Total for activity 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1317496 | 0 | 10539968 | 0 | 14492456 | 15754411 | 0 | 23631648.89 | 26349920 | 39386059.89 | 49.47%
| 4 Project management and communication | 85
1 | Železnice Slovenskej republiky |  | 0 | 0 | 15000 | 0 | 18000 | 0 | 18000 | 3500 | 70000 | 0 | 71000 | 7500 | 75000 | 127000 | 0 | 129000 | 267000 | 267000 | 0%
|  | Total for activity 4 | 0 | 0 | 15000 | 0 | 18000 | 0 | 18000 | 3500 | 70000 | 0 | 71000 | 7500 | 75000 | 127000 | 0 | 129000 | 267000 | 267000 | 0%
| Total eligible costs |  | 0 | 0 | 15000 | 0 | 755798 | 731900 | 924437 | 338600 | 1953598 | 512000 | 11020342 | 28500 | 14874487 | 16313139 | 0 | 24281668.89 | 29543662 | 42205807.89 | 42.86%
1 | Železnice Slovenskej republiky |  | 0 | 0 | 15000 | 0 | 755798 | 731900 | 924437 | 338600 | 1953598 | 512000 | 11020342 | 28500 | 14874487 | 16313139 | 0 | 24281668.89 | 29543662 | 42205807.89 | 42.86%
| Total cumulated eligible costs |  | 0 | 0 | 15000 | 0 | 770798 | 731900 | 1695235 | 1070500 | 3648833 | 1582500 | 14669175 | 1611000 | 29543662 | 17924139 | 29543662 | 42205807.89 | 29543662 | 42205807.89 | 42.86%
1 | Železnice Slovenskej republiky |  | 0 | 0 | 15000 | 0 | 770798 | 731900 | 1695235 | 1070500 | 3648833 | 1582500 | 14669175 | 1611000 | 29543662 | 17924139 | 29543662 | 42205807.89 | 29543662 | 42205807.89 | 42.86%

## Financing needs (€)
Financing needs of the Action 2016-SK-TMC-0218-W (€)
|  |  | 2017 |  | 2018 |  | 2019 |  | 2020 |  | 2021 |  | 2022 |  | 2023 |  | 2024 |  | Total
| Activity name | Funding rate (%) | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Lastest GA in force | Current ASR | Deviation (%)
| 1 Public procurement, authorisation procedures and detailed design | 85
1 | Železnice Slovenskej republiky |  | 0 | 0 | 0 | 0 | 627128.3 | 622115 | 770471.45 | 284835 | 394195.15 | 435200 | 0 | 17850 | 0 | 113900 | 0 | 0 | 1791794.9 | 1473900 | -17.74%
|  | Totals for activity 1 | 0 | 0 | 0 | 0 | 627128.3 | 622115 | 770471.45 | 284835 | 394195.15 | 435200 | 0 | 17850 | 0 | 113900 | 0 | 0 | 1791794.9 | 1473900 | -17.74%
| 2 Construction works and author supervision | 85
1 | Železnice Slovenskej republiky |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 86991.55 | 0 | 347967.9 | 0 | 260976.35 | 253068.8 | 0 | 442867 | 695935.8 | 695935.8 | 1.673e-14%
|  | Totals for activity 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 86991.55 | 0 | 347967.9 | 0 | 260976.35 | 253068.8 | 0 | 442867 | 695935.8 | 695935.8 | 1.673e-14%
| 3 Construction works | 85
1 | Železnice Slovenskej republiky |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1119871.6 | 0 | 8958972.8 | 0 | 12318587.6 | 13391249.35 | 0 | 20086901.5565 | 22397432 | 33478150.9065 | 49.47%
|  | Totals for activity 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1119871.6 | 0 | 8958972.8 | 0 | 12318587.6 | 13391249.35 | 0 | 20086901.5565 | 22397432 | 33478150.9065 | 49.47%
| 4 Project management and communication | 85
1 | Železnice Slovenskej republiky |  | 0 | 0 | 12750 | 0 | 15300 | 0 | 15300 | 2975 | 59500 | 0 | 60350 | 6375 | 63750 | 107950 | 0 | 109650 | 226950 | 226950 | 0%
|  | Totals for activity 4 | 0 | 0 | 12750 | 0 | 15300 | 0 | 15300 | 2975 | 59500 | 0 | 60350 | 6375 | 63750 | 107950 | 0 | 109650 | 226950 | 226950 | 0%
| Total financing needs |  | 0 | 0 | 12750 | 0 | 642428.3 | 622115 | 785771.45 | 287810 | 1660558.3 | 435200 | 9367290.7 | 24225 | 12643313.95 | 13866168.15 | 0 | 20639418.5565 | 25112112.7 | 35874936.7065 | 42.86%
1 | Železnice Slovenskej republiky |  | 0 | 0 | 12750 | 0 | 642428.3 | 622115 | 785771.45 | 287810 | 1660558.3 | 435200 | 9367290.7 | 24225 | 12643313.95 | 13866168.15 | 0 | 20639418.5565 | 25112112.7 | 35874936.7065 | 42.86%
| Total cumulated financing needs |  | 0 | 0 | 12750 | 0 | 655178.3 | 622115 | 1440949.75 | 909925 | 3101508.05 | 1345125 | 12468798.75 | 1369350 | 25112112.7 | 15235518.15 | 25112112.7 | 35874936.7065 | 25112112.7 | 35874936.7065 | 42.86%
1 | Železnice Slovenskej republiky |  | 0 | 0 | 12750 | 0 | 655178.3 | 622115 | 1440949.75 | 909925 | 3101508.05 | 1345125 | 12468798.75 | 1369350 | 25112112.7 | 15235518.15 | 25112112.7 | 35874936.7065 | 25112112.7 | 35874936.7065 | 42.86%

## Progress Overview
Progress Overview of the Action 2016-SK-TMC-0218-W (at accumulated level)
| 2017 |  |  | 2018 |  |  | 2019 |  |  | 2020 |  |  | 2021 |  |  | 2022 |  |  | 2023 |  |  | 2024 |  |  | 2025
| Financial Progress |  | Technical Progress | Financial Progress |  | Technical Progress | Financial Progress |  | Technical Progress | Financial Progress |  | Technical Progress | Financial Progress |  | Technical Progress | Financial Progress |  | Technical Progress | Financial Progress |  | Technical Progress | Financial Progress |  | Technical Progress | Financial Progress |  | Technical Progress
Activity name | Latest GA | Current ASR | Current ASR | Latest GA | Current ASR | Current ASR | Latest GA | Current ASR | Current ASR | Latest GA | Current ASR | Current ASR | Latest GA | Current ASR | Current ASR | Latest GA | Current ASR | Current ASR | Latest GA | Current ASR | Current ASR | Latest GA | Current ASR | Current ASR | Latest GA | Current ASR | Current ASR
Activity 1 | 0 | 0 | 9 | 0 | 0 | 23 | 35 | 46 | 35 | 78 | 68 | 48 | 100 | 100 | 70 | 100 | 100 | 89 | 100 | 100 | 98 | 100 | 100 | 100 | 100 | 100 | 100
Activity 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 62 | 0 | 0 | 100 | 0 | 8 | 100 | 0 | 75 | 100 | 0 | 100
Activity 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 45 | 0 | 0 | 100 | 0 | 38 | 100 | 0 | 100 | 100 | 0 | 100
Activity 4 | 0 | 0 | 0 | 6 | 0 | 20 | 12 | 0 | 30 | 19 | 100 | 60 | 45 | 100 | 60 | 72 | 100 | 60 | 100 | 100 | 60 | 100 | 100 | 60 | 100 | 100 | 100
For the Action | 0 | 0 | 3 | 0 | 0 | 8 | 3 | 46 | 12 | 6 | 68 | 17 | 12 | 100 | 24 | 50 | 100 | 30 | 100 | 100 | 51 | 100 | 100 | 93 | 100 | 100 | 100