Action's planned implementation technical progress (cumulated %)

|  | 2017 |  | 2018 |  |  | 2019 |  |  | 2020 |  |  | 2021 |  |  | 2022 |  |  | 2023 |  |  | 2024 |  |  | 2025 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Action level | Previous ASR | Current ASR |  | Previous ASR | Current ASR |  | Previous ASR | Current ASR |  | Previous ASR | Current ASR |  | Previous ASR | Current ASR |  | Previous ASR | Current ASR |  | Previous ASR | Current ASR |  | Previous ASR | Current ASR |  | Previous ASR | Current ASR |
|  | 3 | 3 |  | 8 | 8 |  | 12 | 12 |  | 17 | 17 |  | 24 | 24 |  | 35 | 30 |  | 74 | 51 |  | 100 | 93 |  | N/A | 100 |
| Activity | Previous ASR | Current ASR |  | Previous ASR | Current ASR |  | Previous ASR | Current ASR |  | Previous ASR | Current ASR |  | Previous ASR | Current ASR |  | Previous ASR | Current ASR |  | Previous ASR | Current ASR |  | Previous ASR | Current ASR |  | Previous ASR | Current ASR |
| 1 | 9 | 9 |  | 23 | 23 |  | 35 | 35 |  | 48 | 48 |  | 70 | 70 |  | 98 | 89 |  | 98 | 98 |  | 100 | 100 |  | N/A | 100 |
| 2 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 1 | 0 |  | 53 | 8 |  | 100 | 75 |  | N/A | 100 |
| 3 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 1 | 0 |  | 68 | 38 |  | 100 | 100 |  | N/A | 100 |
| 4 | 0 | 0 |  | 20 | 20 |  | 30 | 30 |  | 60 | 60 |  | 60 | 60 |  | 60 | 60 |  | 60 | 60 |  | 100 | 60 |  | N/A | 100 |

All the activities and the Action will achieve 100% of technical progress by their actual end dates